## Sheet1
Učešće članova u implementaciji po funkcionalnostima
|  | Storypoints |  | Plan |  |  |  | Stanje na dan 3.2.2025.
[8 empty] | procentualno učešće |  |  |  | Bodovanje učešća
| Opis funkcionalnosti |  | U koje tabele se dodaju (ili mijenjaju) zapisi za navedenu funkcionalnost | Marko | Adnan | Član 3 | Sumarno treba biti 100% | Marko | Adnan | Član 3 |  | Marko | Adnan | Član 3
Artist | Manage music | 3 | Track, ArtistTrack, Album, Notification | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 3 | 0 | 0
| Manage products | 3 | Product, ProductPhoto, Notification | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0 | 3 | 0
| View orders | 2 | (reads from) Orders, OrderDetails | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0 | 2 | 0
| View analytics | 5 | (reads from) Product, Follows, TrackStream | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0 | 5 | 0
Listener | Register, login, auth | 5 | User | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 5 | 0 | 0
| Music streaming | 3 | (reads from) Track | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 3 | 0 | 0
| Manage playlists | 3 | Playlist, TrackPlaylist | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0 | 3 | 0
| Follow artists & Users | 5 | Follows, FollowsForUser | 50% | 50% | 0% | 100% | 50% | 50% | 0% | 100% | 2.5 | 2.5 | 0
| Buy & view products | 6 | Orders, OrderDetails, UserShoppingCart, UserProductWishlist | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0 | 6 | 0
| Manage subscriptions | 3 | Subscriptions | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0 | 3 | 0
| View notifications | 5 | Notification, ReadNotification, MyAppUserPreferences | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 5 | 0 | 0
| Chat | 8 | UserChat, ChatMessage | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 8 | 0 | 0
| Search, Filter, Sort Products in Shop | 5 | (reads from) Product | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0 | 5 | 0
| Share music in app/social media | 5 | ChatMessage | 50% | 50% | 0% | 100% | 50% | 50% | 0% | 100% | 2.5 | 2.5 | 0
Shared | Search | 2 | (reads from) Track, Artist, MyAppUser, Album | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 2 | 0 | 0
| Manage profiles | 5 | Artist, MyAppUser, UserArtist, UserArtistRole, MyUserArtistInvite | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 5 | 0 | 0
| View profiles | 3 | (reads from) Track, Artist, MyAppUser, Product, Event | 25% | 75% | 0% | 100% | 25% | 75% | 0% | 100% | 0.75 | 2.25 | 0
|  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
… |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
|  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
|  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
|  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
|  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
|  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
|  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
|  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
[8 empty] | Ukupni bodovi: |  |  |  | 36.75 | 34.25 | 0
Popis tabela | Da li je obuhvaćena u spisku funkcionalnosti |  | Popis naprednih (dodatnih) funkcionalnosti | Član 2 bodovi
User | TRUE |  | Stripe | 15
Artist | TRUE |  | Slideshow | 3
UserArtist | TRUE |  | Carousell 1 | 3
Track | TRUE |  | Carousell 2 | 3
ArtistTrack | TRUE |  | Social media sharing | 4
Album | TRUE |  | Custom Keyboard Shortcuts | 4
Credits | FALSE |  | Leaflet map | 5
Genres | FALSE |  | User profile picture & Crop | 4
TrackGenre | FALSE |  | Drag & Drop with preview | 6
Playlist | TRUE |  | Zoom | 3
TrackPlaylist | TRUE |  | Prikaz proizvoda sa opcijama | 10
|  |  | Favorites | 2
… | FALSE |  | Prikaz slika | 2
Subscriptions | TRUE |  | Search sa debouncingom | 3
Follows | TRUE |  | Autocomplete | 2
UserArtistRole | TRUE |  | Paywall integracija | 4
Order | TRUE |  | JS Grafikoni za prikaz podataka | 4
OrderDetails | TRUE |  | JS Grafikoni za statistički prikaz podataka | 3
Product | TRUE |  | Korpa | 15
ProductPhoto | TRUE |  | Analytics and Reporting Dashboard | 8
TrackStream | TRUE |  | Angular smooth transitions | 3
Notification | TRUE |  | User activity tracking | 5
ReadNotification | TRUE |  | Reaction System | 2
MyAppUserPreferences | TRUE |  | Ukupno | 111
ChatMessage | TRUE |  | Ukupno sa osnovnim funkcionalnostima | 124
UserChat | TRUE |  | Dodatno | 15
MyUserArtistInvite | TRUE |  | Customizable monthly stats, html2canvas download | 2 + 3
Event | TRUE |  | Server resizing for images | 2
UserOrder | FALSE |  | Collab playlist system + invite per link | 3 + 2
FollowForUser | FALSE |  | Slugs for products | 1
UserShoppingCart | TRUE |  | Sidenav for listener and artist | 2
UserProductWishlist | TRUE
|  |  | Popis naprednih (dodatnih) funkcionalnosti | Član 1 bodovi
|  |  | Multilanguage | 4
|  |  | Slanje tokena za aktivaciju/šifru ili invite friends | 4
|  |  | Background procesi / Scheduler for Recurrent Tasks | 6
|  |  | Drag-and-Drop File Upload with Preview | 6
|  |  | Image/Video Compression Before Upload | 4
|  |  | Spremanje/preuzimanje fajlova (na file sistem) backend | 4
|  |  | Prikaz slika | 3
|  |  | SignalR i real-time messaging | 10
|  |  | Kontinuirano skrolovanje (Infinite Scroll) | 4
|  |  | LiveFilter - Filtriranje u realnom vremenu | 6
|  |  | Implementacija Notifikacija sa statusom pročitano/nepročitano | 3
|  |  | Custom Notification Center | 6
|  |  | Notification Advanced Customization | 4
|  |  | HTTP Interceptor in Angular for API Error Handling | 3
|  |  | Autocomplete u poljima za unos | 2
|  |  | Lazy Loading for Angular Modules | 5
|  |  | Real-Time Data Updates using SignalR in Angular | 8
|  |  | JWT Authentication with .NET Core and Angular | 5
|  |  | JWT Refresh Tokens | 6
|  |  | CRUD Operations with Angular Reactive Forms | 7
|  |  | Caching with .NET Core and Redis | 7
|  |  | Search Functionality with Debouncing in Angular | 3
|  |  | Angular Custom Pipes for Data Transformation | 3
|  |  | Dynamic QR Code Generation for Content Sharing | 4
|  |  | User Profile Picture Upload and Cropping | 4
|  |  | Ukupno | 121
|  |  | Ukupno sa osnovnim funkcionalnostima | 134
|  |  | Dodatno | +8
|  |  | Custom Music Player With Skip, Skip previous, Repeat, Shuffle & Autoplay + Queues, Queue Management(add, remove) and Saved Queues Between Sessions | 8
Navesti stvarni datum stanja